## De-anonymized Data
DPP2 Mandatory Test Cases for Single Berthing PSAC+CCA | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18
Pre-requisite
All Users are available
CRITERIA/PURPOSE
PSAC Terminal creates the Terminal data.
Pilotage and Towage for the PSAC vessel can come from (1) DPP2 API (2) OHS API
Pilotage and Towage VesselID+VesselVoyageNumber can be Matching TermData vesselFullOutVoyN last 6 chars for CCA only
Test Summary Report
Test Environment | PAT
Total Test Count | 123 | 0 | 123 |  | Defect Priority /Total | 0 |  |  | Defect Status | 0 |  |  |  | Test Cases Complex | 121 | Estimated Effort
Not Yet Run | 0 | 0 |  |  | CAT A | 0 |  |  | Assigned | 0 |  |  | S | Simple: may be 15 min | 39 | 1.2188
Passed | 0 | 0 |  |  | CAT B | 0 |  |  | Closed | 0 |  |  | M | Medium: 16 min - 40 min | 82 | 6.8333
Retest Pass | 0 | 0 |  |  | CAT C | 0 |  |  | New | 0 |  |  | C | Complex: 40 min - 60 min | 0 | 0
Failed | 0 | 0 |  |  | NO ISSUE | 0 |  |  | On Hold | 0
Retest Fail | 0 | 0 | [6 empty] | Rejected | 0 |  |  |  | Test Data Preparation Complex | 0 | Estimated Effort
In Progress | 0 | 0 | [6 empty] | Reopened | 0 |  |  | Prep-C | Complex: 31 - 1 hr | 0 | 0
Blocked | 0 | 0 | [6 empty] | Resolved | 0 |  |  | Prep-2C | 2 Complex: 1hr - 2 hr | 0 | 0
| 0 | 0 | [10 empty] | Prep-3C | 3 Complex: 2hr - 3 hr | 0 | 0
Total Execution Rate | 0
Total Remaining | 0
Test Case ID | Test Case Name | Pre-Condition | Actor(s) | Test Data | Step Description | Expected Result | Execution Date | Time used in Mins | Actual Result | Status | Defect ID | Defect Description | Defect Priority | Defect Status | Defect Type | Feedback Type | Remarks | In Scope
Sequence of Creation: DPP2 Pilotage --> DPP2 Towage --> PSAC + CCA TermData (PSAC Terminal will not use smart logic, also use vsl ID + Voyage to match with OHS/DPP2 Pilotage)
Take Note ETB & RTD Logic as below :
Terminal berthing has been created but vessel itinerary has not been created yet.
current - 3 days <= ETB <= current + 3 days (configurable) ----> Online can display this vessel.
ETU ( UBTR/ ATU) < current ----> Agent user can not create vessel itinerary.
current <= ETU ( UBTR/ ATU) or ETU ( ATU) is not exist ----> Agent user can create vessel itinerary.
current <= ETB <= current + 72h (configurable) ----> Agent user can receive notification that alert him to create vessel itinerary.
Terminal berthing has been created and vessel itinerary has been created.
departed_i = N and no RTD ----> Vessel can display & editable.
departed_i = N and has RTD ----> Vessel can display & can not editable.
departed_i = Y and has RTD ----> Vessel can not display.
departed_i = Y and no RTD ----> Vessel can not display.
REGRESSION TEST for Singe Berthing of PSAC Terminal, CCA Agent
TC_PSAC_S01 | [DPP2 Terminal Berthing API - Create Terminal Data with SEQ1 record ] - Have BTR, UBTR, ETB, no ETU - SEQ1 (Location P10) - with current <= ETB <= current + 72 hours | Avail Dates in vessel: BTR, UBTR, ETB | PSAC Terminal |  | Craft Create Terminal Data JSON message and run in Postman - with current <= ETB <= current + 3 days | 1. Terminal Data for SEQ1 created successfully. 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 Note: for MODIFIER_ID,MODIFIER_ORG_C upon creation is empty but shortly after the creation email is send out it will become PCSYS as the BE batch job update the record with the notifyEtb_dt fields | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S02 | [Online - Enquire Terminal Data Vessel Itinerary page after creation] |  | CCA Agent |  | Agent check Vessel Itinerary Page | Agent user can View and Create vessel itinerary for Terminal Data . Agent check Vessel Itinerary Page Header's Berthing time shows Seq1 ETB, Unberthing time shows Seq1 UBTR Berthing SRT = BTR, Start Time = ETB Unberthing SRT = UBTR, End time = blank as no ETU - At the right side, there is a 3dot icon, showing "Create" option - all info showing correctly (only have Berthing, Unberthing records) - Vessel Itinerary is not Submit Icon display Red as Itinerary Details still need to be submitted by user. 2. All the dates are correct, as per JSON | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S03 | [Email - Agent received email notification on Vessel Itinerary creation] - with (current <= ETB <= current + 3 days ) ] |  | CCA Agent |  | Agent check mailbox Note: If ETB is past timing, notification won't be trigger for outdated. | Email notification on TermData creation is received based on ETB timing with future timing and within 3 days. - the information in the email is correct. - 1 emails received. Subject [JIT] Creation of Vessel Itinerary | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S04 | [DB - Enquire Terminal Data & Agent Vessel Call record] - Check No Vessel Itinerary is auto-generated |  | DPP2 Admin |  | 1. Go to the DB and retrieve the vessel created by PSAC. Check the field VIID and other columns details | 1. Create record for Terminal Berthing successfully, with No record of vessel VIID autogenerated in AGENT_VESSEL_CALL tables 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 select * from Terminal_berthing where vsl_id = '2292605' ; SELECT AGENT_VESSEL_CALL_ID, VSL_M, VOY_N, RTA_DT from AGENT_VESSEL_CALL where VSL_M¦¦'/'¦¦VOY_N = 'LHPSA2BER V0928/OUTV9266'; | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S05 | [DPP2 API - Update Terminal Data with SEQ1 record ] - Add ETU timing - So now have BTR, UBTR, ETB, ETU - ETU = Current + 2 days | Avail Dates in vessel: BTR, UBTR, ETB, ETU | PSAC Terminal |  | Craft Update Terminal Data JSON message and run in Postman - with ETU = Current + 2 days | 1. Terminal Data for SEQ1 ETU updated successfully. | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S06 | [DPP2 API - Create Pilotage Order Inbound (location is PEBGA to P10)] | Use Vessel ID + Voyage to match with Terminal data | PSA Marine |  | DPP2 API - Create Pilotage Order (Inbound) - e.g. PEBGA to P10 Note: - VesselAbbrName cannot > 17 chars - OHS Pilotage INBOUND with same vessel id & voyage number of last 6 chars from Terminal for CCA - for INBOUND Pilotage (both SRT, CST exist ) CST is better before ETB/ ATB with Terminal data - "adviceC": "N" | 1. Pilotage Order for Inbound created successfully via API 2. Records displayed in DPP2 Vessel Itinerary Page 3. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S07 | [OHS API /DPP2 API - Create Pilotage Order Outbound (location is P10 to SEAW)] |  | PSA Marine |  | DPP2 API - Create Pilotage Order (Outbound) - e.g. P10 to SEAW via OHS API Note: - VesselAbbrName cannot > 17 chars - OHS Pilotage OUTBOUND with same vessel id & voyage number of last 6 chars from Terminal for CCA - for OUTBOUND Pilotage only SRT exist and is better after ubtr / ETU / ATU with Terminal data - "adviceC": "N" | 1. Pilotage Order for Outbound created successfully via API 2. Records displayed in DPP2 Vessel Itinerary Page 3. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S08 | [DPP2 API - Create Towage Order Inbound (location is PEBGA to P10)] |  | PSA Marine |  | DPP2 API - Create Towage Order (Inbound) - e.g. PEBGA to P10 Note: - OHS Towage INBOUND with same vessel id & voyage number of last 6 chars from Terminal - for INBOUND Towage CST is better before ETB/ ATB with Terminal data - "adviceC": "C" | 1. Towage Order for Inbound created successfully via API 2. Records displayed in DPP2 Vessel Itinerary Page 3. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S09 | [DPP2 API - Create Towage Order Outbound (location is P10 to SEAW)] |  | PSA Marine |  | DPP2 API - Create Towage Order (Outbound) - e.g. P10 to SEAW Note: - OHS Towage OUTBOUND with same vessel id & voyage number of last 6 chars from Terminal - for OUTBOUND Towage SRT is better after ubtr / ETU /ATU with Terminal data - "adviceC": "C" | 1. Towage Order for Outbound created successfully via API 2. Records displayed in DPP2 Vessel Itinerary Page 3. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S10 | [Online - Check Vessel Itinerary page after Pilotage and Towage come in and ETU added] |  | CCA Agent |  | Check all pages and ensure info correct | Agent check Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 2 x Pilotage, 2 x Towage, Activity sorting correct) Header's Berthing time = ETB, Unberthing time = ETU Berthing SRT = BTR, Start Time = ETB Unberthing SRT = UBTR, End time = ETU Vessel Itinerary Submit Icon is red as Vessel Itinerary is not submit At the right side, there is a 3dot icon, showing "Create" option All activity is sorted correctly based on its SRT Agent check Dashboard (Check status, Check listing of activities) No vessel found as the Vessel Itinerary is not submit Any bunker provider (BAS or INS) check Bunkering Page No vessel found as the vessel does not have any towage activity belong to towage provider (BAS or INS) Any towage provider (ANU or AAU) check Towage Page No vessel found as the vessel does not have any towage activity belong to towage provider (ANU or AAU) Any supplies provider (USW or YCP) check Supplies Page no vessel found as the vessel does not have any towage activity belong to towage provider (USW or YCP) | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S11 | [Online - Agent Submit Vessel Itinerary] - click on 3dot > +Create, click SAVE without make any changes |  | CCA Agent |  | 1. Agent click on 3 dots > Create, do not add activities 2. Click Save button | Agent check Vessel Itinerary Details Page (if no ETA, once first Submit Vessel Itinerary Estimated Time of Arrival = ETB of Terminal data, which will save ETB value into Agent_Vessel_Call.ETA ) Estimated Time of Unberthing = ETU Sorting of the activities are the same as Vessel Itinerary page After Save the Vessel Itinerary display submit Successfully and back to Vessel Itinerary page with all records refreshed. | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S12 | [Online - Enquire Vessel Itinerary page after agent submitted Vessel Itinerary] |  | CCA Agent |  | 1. Agent check Vessel Itinerary page after agent submitted Vessel Itinerary | Agent check Vessel Itinerary Page after save "Vessel Itinerary Submitted" Icon is Green after Vessel Itinerary submit At the right side, there is a 3dot icon, showing "Edit" and "Delete" options All activity is sorted correctly based on its SRT Agent check Dashboard - after submit vessel itinerary, vessel displayed and all activities icon and info sequence display correct. Vessel listing box: default is expanded but user can collapse the box (change from v2.10) (Check status, Check listing of activities, can collapse the vessel record) ETA date = ETB, Status is Arriving Activity sequence and timings display correctly The blue or red colour timings: - Actual timing will compare with planned timing and planning timing will compare to current timing - Pilotage & towage Planned start = CST, no planned end timing - If no timing to compare = on time Any bunker provider (BAS or INS) check Bunkering Page No vessel found as the vessel does not have any bunker activity belong to bunker provider (BAS or INS) Any towage provider (ANU or AAU) check Towage Page No vessel found as the vessel does not have any towage activity belong to towage provider (ANU or AAU) Any supplies provider (USW or YCP) check Supplies Page no vessel found as the vessel does not have any supplies activity belong to supplies provider (USW or YCP) | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S13 | [Online - Vessel Itinerary Details] - after add email, click on Envelope |  | Agent & Ship master |  | Agent Enter the ship master email and Click the envelope icon | Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S14 | [Online - Vessel Itinerary Details, add Bunkering at Berth Location activity] - to INS |  | CCA Agent |  | Agent open Vessel Itinerary Details by click on 3 dots > Edit, - add Bunkering to nominate INS company Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered Activity Window default after select BUNKERING - Activity: BUNKERING - Service Provider: Default blank - Service Request Time: Default blank - Location: Default blank - Suggested Activity Duration showing correctly P10 : ETB+1 hrs, ETU-2hrs "OK" and "Cancel" buttons are enabled | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S15 | [Online - error display when Bunkering SRT out of Bunkering Suggest Activity Duration] |  | CCA Agent |  | Agent enter the Bunkering details (SRT OUTSIDE activity window) note: The suggested duration is take from either Btr/uBtr if both planning & actual does not exist Planned timing if actual does not exist or actual timing is before planned timing actual timing if there is actual timing and it after planned timing. These rules are apply since one of the CR on multiple berthing handling. the 1 hour and 2 hours is configurable | Check on Add / Update Bunkering Activity page Suggested Activity Duration: Ber1( ETB +1 hour to ETU-2 hours), e.g.: P10(22 Jun 2022 14:30 - 24 Jun 2022 21:30) Error prompted within the popup and Agent is unable to add Bunkering activity | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S16 | [Online - Vessel Itinerary Details, add Towage activity] - to ANU |  | CCA Agent |  | Continue on Vessel Itinerary Details page - add Towage to nominate ANU company Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S17 | [Online - Vessel Itinerary Details, add Supplies activity] - to USW |  | CCA Agent |  | Continue on Vessel Itinerary Details page - add Supplies to nominate USW company Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered Activity Window default after select SUPPLIES - Service Provider: Default blank - Service Request Time: Default blank - Location: Default blank - Suggested Activity Duration showing correctly P10 : ETB+1 hrs, ETU-2hrs "OK" and "Cancel" buttons are enabled | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S18 | [Online - Vessel Itinerary Details, add Bunkering at Anchorage Location activity] - to INS |  | CCA Agent |  | Continue on Vessel Itinerary Details page - add Bunkering to nominate INS company - Input a anchorage location e.g. PEBGA Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered Activity Window default after select BUNKERING - Activity: BUNKERING - Service Provider: Default blank - Service Request Time: Default blank - Location: Default blank No Suggested Activity Duration showing "OK" and "Cancel" buttons are enabled | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S19 | [Online - Vessel Itinerary Details, add Supplies at Anchorage Location activity] - to USW |  | CCA Agent |  | Continue on Vessel Itinerary Details page - add Supplies to nominate USW company - Input a anchorage location e.g. PEBGA Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered Activity Window default after select SUPPLIES - Service Provider: Default blank - Service Request Time: Default blank - Location: Default blank No Suggested Activity Duration showing "OK" and "Cancel" buttons are enabled | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S20 | [Online - Save Vessel Itinerary Details, after add INS, ANU, USW activities] |  | CCA Agent |  | Continue on Vessel Itinerary Details page : Click on SAVE button after add INS, ANU, USW activities | Agent Check Vessel Itinerary Details Page The activities with service provider shown correctly as entered After Save the Vessel Itinerary, display save Successfully and back to Vessel Itinerary page with all records refreshed. | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S21 | [Online - Check all pages] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Agent Check Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 4 x Towage, 2 x Bunkering, 2 x Supplies, Activity sorting) All activity with service provider shown correctly All activities are sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Newly added bunkering, towage and supplies activities displayed correctly. Agent check Vessel Itinerary Details - same info as Vessel Itinerary Agent and Service Providers check Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) No Supporting vessels icon displayed ETA date = ETB, Status is Arriving Katalon pages comparison for INS, ANU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S22 | [DB - Enquire Terminal Data & Agent Vessel Call record after Vessel Itinerary Submit] - Check for VIID generated after submit Vessel Itinerary - Check for Active_I=‘Y' |  | DPP2 Admin |  | 1. Go to the DB and retrieve the vessel created by PSAC. Check the field VIID and other columns details | 1. Create record Vessel Itinerary , with VIID created and Active_I = 'Y' 2. Terminal Berthing Table no change. 3. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 Note: AGENT_VESSEL_CALL.Terminal_C =terminal_berthing.CREATOR_ORG_C select * from Terminal_berthing where vsl_id = '2292605' ; SELECT AGENT_VESSEL_CALL_ID, VSL_M, VOY_N, RTA_DT from AGENT_VESSEL_CALL where VSL_M¦¦'/'¦¦VOY_N = 'LHPSA2BER V0928/OUTV9266'; | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S23 | [Email - INS, USW, ANU received Bunkering & Supplies & Towage emails notification as it is nominated by agent ] |  | INS, USW, ANU User |  | Bunkering & Supplies & Towage Service Provider check mailbox | 5 emails sent to the service providers - INS receive 1 email for been nominated by agent as provider for Bunkering at Berth Location. Email Title: [JIT] Bunkering Activity was Created - INS receive 1 email for been nominated by agent as provider for Bunkering at Anchorage Location. Email Title: [JIT] Bunkering Activity was Created - USW receive 1 email for been nominated by agent as provider for Bunkering at Berth Location. Email Title: [JIT] Bunkering Activity was Created - USW receive 1 email for been nominated by agent as provider for Bunkering at Anchorage Location. Email Title: [JIT] Bunkering Activity was Created - ANU receive 1 email for been nominated as provider for Towage. Email Title: [JIT] Towage Activity was Created | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S24 | [Online - INS Update Bunkering at Berth Location ] - add CST |  | INS user ID |  | INS Update Bunkering to add CST Bunkering Planned Start = CST Bunkering Planned End = Suggestion duration End | Vessel Itinerary alert icon for Bunkering activity is white filled circle Bunkering activity showing Confirm Service Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S25 | [Online - ANU Update Towage ] - add CST |  | ANU user ID |  | ANU Update Towage to add CST Towage CST = Agent SRT + 10 min Towage Actual Start, Actual End = blank | Vessel Itinerary alert icon for Towage activity is white filled circle. Towage activity showing Confirm Service Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S26 | [Online - USW Update Supplies at Berth Location ] - add CST |  | USW user ID |  | USW Update Supplies to add CST | Vessel Itinerary alert icon for Supplies activity is white filled circle. Supplies activity showing Confirm Service Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S27 | [Online - INS Update Bunkering at Anchorage Location ] - add CST |  | INS user ID |  | INS Update Bunkering to add CST Bunkering Planned Start = CST Bunkering Planned End = Suggestion duration End | Vessel Itinerary alert icon for Bunkering activity is white filled circle Bunkering activity showing Confirm Service Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S28 | [Online - USW Update Supplies at Anchorage Location ] - add CST |  | USW user ID |  | USW Update Supplies to add CST | Vessel Itinerary alert icon for Supplies activity is white filled circle. Supplies activity showing Confirm Service Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S29 | [Online - Check all pages] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Agent Check Vessel Itinerary Page (2 x Berthing, 2 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 3 x Towage, 2 x Bunkering, 2 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Vessel Itinerary Details - same info as Vessel Itinerary Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) No Supporting vessels icon displayed Status is Arriving , ETA date = ETB Katalon pages comparison for INS, ANU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S30 | [Email - Agent receive notification of CST change] |  | ANU/ INS user ID |  | Agent check mailbox | Agent received 5 emails e.g. Email Title: 2 x [JIT] Update in Bunkering CST 1 x [JIT] Update in Towage CST 2 x [JIT] Update in Supplies CST | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S31 | [Online & DB ] - No History after activities creation and 1st update |  | PMP |  | 1. Expand the history records on Vessel Itinerary details page 2. DB check above Activities history via SQL | 1. Check Vessel Itinerary Details Page under New Create activities should display blank history (the creation and 1st update no history display via online) 2. Check DB history table should exist records same with 1st update activities. | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S32 | [DPP2 Terminal API - SEQ1 ETB change] - Change the ETB to earlier or later date time, (More than 30 min BEFORE old ETB) |  | PSAC Terminal |  | Update TermData API, and set Seq1: ETB > old ETB more than 30 mins | 1. Terminal Data for SEQ1 ETB updated successfully. | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S33 | [Online - Check all pages] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) - Expecting to see red alert and blue alert in all pages |  | Agent & Svc Provider: INS, ANU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Note: 1) ETA is supposed to be from MDH. However, in GIT UAT environment, there is no such endpoint. 2) During creation, when there is no such endpoint, the system will derive ETA from ETB. this logic "ETA is currently taking ETB value upon creation" itself is an backup logic as there is no MDH in GIT UAT. The actual logic is always to take from MDH during creation / update and batch job update Check Dashboard for Service Providers Run Katalon | Agent Check Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 3 x Towage, 2 x Bunkering, 2 x Supplies, Activity sorting correct) Header's Berthing Time = ETB Berthing activity start time = ETB Vessel has a red alert, and activities created online have blue alert, i.e. blue filled circle All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Agent Check Vessel Itinerary Details Page ETA remains as OLD ETB Berthing Activity (in the header & details) shows NEW ETB The History for ETB update exist under the Berthing activity Agent and Service Providers Check Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) No Supporting vessels icon displayed Status is Arriving , ETA date = ETB Katalon pages comparison for INS, ANU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S34 | [Email - Agent & Svc provider receive notification of ETB Change] - as the ETB change will impact them |  | Agent & Svc Provider INS, ANU |  | Agent and Svc provider check email about ETB changed | Check auto-notification email sent to agent & Svc provider (Service Providers INS, ANU, USW, Agent received email) Email Title: [JIT] Update in Vessel ETB - Agent: 1 email - Svc provider: 1 per distinct activity service provider orgC | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S35 | [Online - Vessel Itinerary Details, after ETB update] - click on Envelope |  | CCA Agent |  | Agent click on Envelope | Message "Email sent successful" appeared | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S36 | [Email - Agent & Ship master received email - after ETB update] |  | Agent & Ship master |  | Agent Enter the ship master email and Click the envelope icon | Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S37 | [Online - INS Update Bunkering + Acknowledge] - update CST, Craft Name & Licence number, Planned Start, Planned End, then acknowledge |  | INS Bunkering Svc Provider |  | INS update CST within suggested duration and Planned Start <= [Current + 1 hr (config)], Craft Name & Licence number, Planned Start, Planned End, then acknowledge - add valid Craft Licence number that starts with SB Note: When both craft name & licence no. is provided. System will only validate using licence no. and auto update the craft name base on the licence no. This is because there can have multiple record with same craft name but the licence no. is unique | JIT Bunkering page: Bunkering saved and acknowledged successfully. Bunkering alert icon for Bunkering activity becomes original white filled circle. Bunkering activity showing new Confirm Service Time, Craft Name and Licence, Planned Start and Planned End | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S38 | [Online - Error displayed when INS Update Bunkering at Berth Location Craft Licence number which DOES NOT start with SB] |  | INS Bunkering Svc Provider |  | INS update Craft Licence number and click OK - add Craft Licence number that does not with SB | Error displayed and bunkering activity cannot be updated successfully | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S39 | [Online - ANU Update Towage + Acknowledge] - update CST, 1 x (Tug ID & Tug Name), then acknowledge |  | ANU Towage Svc Provider |  | ANU update CST <= [Current + 1 hr (config)], 1 x ( Tug ID & Tug Name), then acknowledge - add valid Craft Licence number that starts with ST | JIT Towage page: Towage saved and acknowledged successfully. Towage alert icon for Towage activity becomes original white filled circle. Towage activity showing new Confirm Service Time, Tug Name and Licence | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S40 | [Online - Error displayed when ANU Update Towage Craft Licence number which DOES NOT start with ST] |  | ANU Towage Svc Provider |  | ANU update Craft Licence number and click OK - add Craft Licence number that does not with ST | Error displayed and towage activity cannot be updated successfully | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S41 | [Online - USW Update Supplies at Berth Location + Acknowledge] - update CST, Craft Name & Licence number, Planned Start, Planned End, then acknowledge |  | USW Supplies Svc Provider |  | USW update CST <= [Current + 1 hr (config)] , Craft Name & Licence number, Planned Start, Planned End, then acknowledge | JIT Supplies page: Supplies saved and acknowledged successfully. Supplies alert icon for Supplies activity becomes original white filled circle. Supplies activity showing new Confirm Service Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S42 | [Online - Error displayed when USW Update Supplies at Berth Location Craft Licence number which DOES NOT start with SC] |  | ANU Towage Svc Provider |  | ANU update Craft Licence number and click OK - add Craft Licence number that does not with SC | Error displayed and towage activity cannot be updated successfully | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S43 | [Online - INS Update Bunkering at Anchorage Location + Acknowledge] - update CST, Craft Name & Licence number, Planned Start, Planned End, then acknowledge |  | INS Bunkering Svc Provider |  | INS update CST within suggested duration and Planned Start <= [Current + 1 hr (config)], Craft Name & Licence number, Planned Start, Planned End, then acknowledge - add valid Craft Licence number that starts with SB Note: When both craft name & licence no. is provided. System will only validate using licence no. and auto update the craft name base on the licence no. This is because there can have multiple record with same craft name but the licence no. is unique | JIT Bunkering page: Bunkering at Anchorage location saved and acknowledged successfully. Bunkering alert icon for Bunkering activity becomes original white filled circle. Bunkering activity showing new Confirm Service Time, Craft Name and Licence, Planned Start and Planned End | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S44 | [Online - Error displayed when INS Update Bunkering at Anchorage Location Craft Licence number which DOES NOT start with SB] |  | INS Bunkering Svc Provider |  | INS update Craft Licence number and click OK - add Craft Licence number that does not with SB | Error displayed and bunkering activity cannot be updated successfully | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S45 | [Online - USW Update Supplies at Anchorage Location + Acknowledge] - update CST, Craft Name & Licence number, Planned Start, Planned End, then acknowledge |  | USW Supplies Svc Provider |  | USW update CST <= [Current + 1 hr (config)] , Craft Name & Licence number, Planned Start, Planned End, then acknowledge | JIT Supplies page: Supplies at Anchorage location saved and acknowledged successfully. Supplies alert icon for Supplies activity becomes original white filled circle. Supplies activity showing new Confirm Service Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S46 | [Online - Error displayed when USW Update Supplies at Anchorage Location Craft Licence number which DOES NOT start with SC] |  | ANU Towage Svc Provider |  | ANU update Craft Licence number and click OK - add Craft Licence number that does not with SC | Error displayed and towage activity cannot be updated successfully | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S47 | [Online - Check all pages after Update and Acknowledge] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Send Email to Ship Master Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | Agent & Svc Provider: INS, ANU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Note: 1) ETA is supposed to be from MDH. However, in GIT UAT environment, there is no such endpoint. 2) During creation, when there is no such endpoint, the system will derive ETA from ETB. this logic "ETA is currently taking ETB value upon creation" itself is an backup logic as there is no MDH in GIT UAT. The actual logic is always to take from MDH during creation / update and batch job update Send Email to Ship Master Check Dashboard for Service Providers Run Katalon | Agent Check Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 3 x Towage, 2 x Bunkering, 2 x Supplies, Activity sorting correct) The red alert and blue alerts will disappear as all service provider have acknowledged All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Agent Check Vessel Itinerary Details Page - same info as Vessel Itinerary Check notification email sent to ship master All activities updated showing the correct date time. Agent and Service Providers Check Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) Supporting vessels have 2 Bunkering (green icon), 2 Towage (blue icon), 2 Supplies (purple icon) icon appeared (Note: Bunkering & Supplies Supporting Vessel: when [Craft Licence Number exist] + current time fall in [Actual Start > Planned > CST > SRT - 1hr(config) until actual end time] Towage Supporting Vessel: when [Craft Licence Number exist] + current time fall in [CST/Actual start time - 1hr(config) until actual end time]) Status is Arriving , ETA date = ETB Katalon pages comparison for INS, ANU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S48 | [Email - Agent received notification on Service provider Acknowledgement] |  | CCA Agent |  | Agent check email about CST changed & acknowledged | Agent received email e.g. Email Title: 2 x [JIT] Bunkering Activity was Acknowledged 1 x [JIT] Towage Activity was Acknowledged 2 x [JIT] Supplies Activity was Acknowledged | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S49 | [Email - Agent receive notification of CST change] |  | CCA Agent |  | Agent check email about CST changed & acknowledged | Agent received email e.g. Email Title: 2 x [JIT] Update in Bunkering CST 1 x [JIT] Update in Towage CST 2 x [JIT] Update in Supplies CST | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S50 | [Online - Vessel Itinerary Details, add Bunkering at Berth Location activity] - to BAS | Add another set of Bunkering, Towage, Supplies activity - to ensure SP cannot edit another SP job | CCA Agent |  | Agent open Vessel Itinerary Details by click on 3 dots > Edit, - add Bunkering to nominate BAS company Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S51 | [Online - Vessel Itinerary Details, add Towage activity with From and To Location] - to AAU |  | CCA Agent |  | Continue on Vessel Itinerary Details page: - add Towage to nominate AAU company Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S52 | [Online - Vessel Itinerary Details, add Supplies at Berth Location activity] - to YCP |  | CCA Agent |  | Continue on Vessel Itinerary Details page: - add Supplies to nominate YCP company Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S53 | [Online - Vessel Itinerary Details, add Bunkering at Anchorage Location activity] - to BAS | Add another set of Bunkering, Towage, Supplies activity - to ensure SP cannot edit another SP job | CCA Agent |  | Continue on Vessel Itinerary Details page: - add Bunkering to nominate BAS company Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S54 | [Online - Vessel Itinerary Details, add Supplies at Anchorage Location activity] - to YCP |  | CCA Agent |  | Continue on Vessel Itinerary Details page: - add Supplies to nominate YCP company Note: Do not click on SAVE button | Agent Check Vessel Itinerary Details Page The activity with service provider shown correctly as entered | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S55 | [Online - Save Vessel Itinerary Details, add new set of BAS, AAU, YCP activities ] |  | CCA Agent |  | Continue on Vessel Itinerary Details page : Then click on SAVE button after add new set of BAS, AAU, YCP activities | Agent Check Vessel Itinerary Details Page The activities with service provider shown correctly as entered After Save the Vessel Itinerary display save Successfully and back to Vessel Itinerary page with all records refreshed. | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S56 | [Online - Check all pages after BAS, AAU, YCP activities added] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU BAS, AAU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers (BAS, AAU, YCP - now can view Dashboard) Run Katalon | Agent Check Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 5 x Towage, 4 x Bunkering, 4 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) BAS bunkering and AAU towage activities added correctly Agent check Vessel Itinerary Details - same info as Vessel Itinerary Agent and all Service Providers Check Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record ) Supporting vessels have 2 Bunkering (green icon), 2 Towage (blue icon), 2 Supplies (purple icon) icon appeared Status is Arriving, ETA date = ETB Service Provider pages Ensure all service providers only see 3dot on their own service order. e.g. ANU towage will not have 3dot when AAU checking their vessel's towage Katalon pages comparison for INS, BAS, ANU, AAU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S57 | [Email - BAS, AAU, YCP received Bunkering & Towage & Supplies emails notification]] |  | BAS, AAU User |  | Bunkering & Supplies & Towage Service Provider check mailbox | Service Providers BAS, AAU, YCP received email e.g. Email Title: 2 x BAS receive: [JIT] Bunkering Activity was Created 1 x AAU receive: [JIT] Towage Activity was Created 2 x YCP receive: [JIT] Supplies Activity was Created | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S58 | [Online & DB] - History after activities 2nd update INS, ANU, USW - Have 1 line history as CST was updated, so got 1 change. BAS, AAU, YCP - 0 line history cause no changes at all |  | PMP |  | 1. Expand the history records on Vessel Itinerary details page 2. DB check above Activities history via SQL | 1. Check Vessel Itinerary Details Page under New Create activities should display blank history (the creation and 1st update no history display via online) 2. Check DB history table should exist records same with 1st update activities. | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S59 | [Online - Vessel Itinerary Details] - click on Envelope |  | CCA Agent Ship Master |  | Agent click on Envelope | Message "Email sent successful" appeared Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S60 | [DB - Update RTA] - Update in the DB the Reported Time of Arrival | Vessel is In port that activity can fulfill wit h actual timing | PSA Marine |  | Update RTA via DB refer to DB SQL Sheet | RTA updated successfully | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S61 | [DPP2 API - Start Pilotage Inbound] - Update Onboard Date, Start Time. No end time - OrderNumber is same with Pilotage Order | Pilotage onboard | Service Provider PSAM |  | DPP2 API - Update INBOUND Pilotage for PEBGA to P10 - Update Onboard Date, Start Time, No end time - "adviceC": "A" | 1. Pilotage Service for Inbound Pilotage Order updated successfully via OHS API 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S62 | [DPP2 API - Start Towage Inbound] - Update Start Time, and add in 4 tugs details. No end time - OrderNumber is same with Towage Order |  | Service Provider PSAM |  | DPP2 API - Update INBOUND Towage for PEBGA to P10 - Update Start Time, and add in 4 tugs details. No end time "adviceC": "U" | 1. Towage Order for Inbound updated successfully via OHS API/DPP2 API 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 3. Check Dashboard will display an Blue supporting vessel for the 4 Tugs after fill in the actual Start Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S63 | [Online - Check all pages after RTA update, Pilotage Order (IN) and Towage Order (IN) started] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) - Estimated Port Stay is showing the correct timing difference from RTA to NOW |  | CCA Agent INS, ANU BAS, AAU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 5 x Towage, 4 x Bunkering, 4 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Vessel Itinerary Details - same info as Vessel Itinerary Dashboard - vessel displayed and all activities icon and info sequence display correct. Estimated Port Stay is showing the correct timing difference between RTA and NOW (Check status, Check listing of activities, can collapse the vessel record ) Circle in blue filled for towage (IN) n pilotage (IN). Supporting vessels have 2 Bunkering (green icon), 6 Towage (blue icon), 2 Supplies (purple icon) icon appeared (Note: Bunkering & Supplies Supporting Vessel: when [Craft Licence Number exist] + current time fall in [Actual Start > Planned > CST > SRT - 1hr(config) until actual end time] Towage Supporting Vessel: when [Craft Licence Number exist] + current time fall in [CST/Actual start time - 1hr(config) until actual end time]) Status = In Port POB (IN): 26 Nov 2022 15:40 ETB: 26 Nov 2022 16:30 (P10) Katalon pages comparison for INS, BAS, ANU, AAU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S64 | [Online - Vessel Itinerary Details, after RTA, Pilotage and Towage update] - click on Envelope |  | CCA Agent Ship Master |  | Agent click on Envelope | Message "Email sent successful" appeared Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S65 | [DPP2 API - Complete Pilotage Service Inbound] - Update Actual End time - OrderNumber is same with Pilotage Order |  | Service Provider PSAM |  | DPP2 API - Update INBOUND Pilotage Service for PEBGA to P10 - Update Actual End time - "adviceC": "A" | 1. Pilotage Service for Inbound Pilotage Order updated successfully via API 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S66 | [DPP2 API - Complete Towage Service Inbound] - Update 4 tugs Actual End time - OrderNumber is same with Towage Order |  | Service Provider PSAM |  | DPP2 API - Update INBOUND Towage Service for PEBGA to P10 - Update 4 tugs Actual End time - "adviceC": "U" | 1. Towage Order for Inbound updated successfully via API 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 3. Check Dashboard the Blue supporting vessel for the 4 Tugs will disappear after fill in Actual End Timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S67 | [Online - Check all pages after Pilotage Order (IN) and Towage Order (IN) completed] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU BAS, AAU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 5 x Towage, 4 x Bunkering, 4 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Vessel Itinerary Details - same info as Vessel Itinerary Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) Circle in green filled for towage (IN) n pilotage (IN). Supporting vessels have 2 Bunkering (green icon), 2 Towage (blue icon), 2 Supplies (purple icon) icon appeared Status = In Port POB (IN): 26 Nov 2022 15:40 ETB: 26 Nov 2022 16:30 (P10) Katalon pages comparison for INS, BAS, ANU, AAU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S68 | [Online - Check History inside Vessel Itinerary Details] - History after pilotage and towage have been updated PSAM Pilotage - Have 1 line history as Start Time, Arrival Time updated PSAM Towage - Have 1 line history as Start Time, Arrival Time, and number of tugs updated |  | PMP |  | 1. Check above updated Activities via online 2. Check above updated Activities via DB | 1. Check Vessel Itinerary Details Page under activities should display the correct info in history 2. Check DB history table should exist records with history activities. | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S69 | [DPP2 Terminal API - Update Terminal Data record ATB] - SEQ1 (Location P10) - Update ATB to an earlier or later date time, but it must be more than 30 min from the original ATB. Recommended is before current time. | ATB only can be trigger mail only once | PSA Terminal |  | 1. Craft Update Terminal JSON message and run in Postman - Execute JSON for Seq1 first - btrDt is mandatory, ubtrDt exist - etbDt exist, etuDt =exist - atbDt exist, atuDt =not exist Note: If ATB is past timing (current-6) , notification won't be trigger for outdated 6 hours. | 1. Terminal Data for SEQ1 ATB updated successfully. | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S70 | [Online - Check all pages after ATB updated] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers |  | CCA Agent INS, ANU BAS, AAU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 5 x Towage, 4 x Bunkering, 4 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Header's Berthing Time = ATB Berthing activity start time = ATB Vessel Itinerary Details - same info as Vessel Itinerary Actual Time of Berthing = ATB Estimated Time of Arrival remains as ETB Berthing Activity (in the header & details) shows ATB Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) Supporting vessels have 2 Bunkering (green icon) , 2 Towage (blue icon), 2 Supplies (purple icon) icon appeared Status = In Port, ATB: 26 Mar 2023 14:32 (P10) ETU: 31 Mar 2023 09:59 (P10) | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S71 | [Online - Vessel Itinerary Details, after ATB update] - click on Envelope |  | CCA Agent Ship Master |  | Agent click on Envelope | Message "Email sent successful" appeared Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S72 | [Email - Notification after ATB update] - ATB exist |  | CCA Agent |  | Check Agent and Service Provider email note: (current time - 6hrs) <ATB/ATU< current time | Message "Email sent successful" appeared Terminal ATB / ATU first creation will sent 1 mail to ship agent and count of activities ORGC mails to Service Provider [JIT] Vessel ATB | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S73 | [Online - ANU starts Towage Order] - Update Actual Start timing with 4 Tugs info |  | ANU Towage Svc Provider |  | ANU User login to fulfill actual Start timing as Past Timing and 4 Tugs Craft Name & Craft License Number as follows: - At least one of the tugs have only craft licence number, leave craft name blank - All 4 tugs should have UNIQUE craft licence number that starts with ST Note: - When both craft name & licence no. is provided. System will only validate using licence no. and auto update the craft name base on the licence no. - System can complete the information if just has Craft Licence number | 1. ANU Towage was saved successfully 2. Online display the Towage info correctly as updated. 3. Check Dashboard will display a Blue supporting vessel for the 4 Tug after fill in the actual Start Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S74 | [Online - Error displayed when ANU updates 4 Tugs with duplicate Craft Licence Number] |  | ANU Towage Svc Provider |  | ANU User update 4 Tugs Craft Name & Craft License Number - update 4 DUPLICATE valid Craft Licence Number that starts with ST | Error displayed and towage activity cannot be updated successfully | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S75 | [Online - INS starts Bunkering at Berth Location] - Update Actual Start timing & Update Craft Name with no Craft Licence number |  | INS Bunkering Svc Provider |  | INS User login to fulfill actual Start timing as Past Timing INS updates valid Craft Name and leave Craft Licence number blank Note: - system can complete the information if it just has one of Craft Name or Craft Licence number | 1. INS Bunkering was saved successfully 2. Check the updated bunkering info on Bunkering page (icon changed to In progress) 3. Check Dashboard will display a Green supporting vessel after fill in actual Start timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S76 | [Online - INS starts Bunkering at Berth Location] - Update Actual Start timing & Update Craft Licence number with no Craft Name |  | INS Bunkering Svc Provider |  | INS User login to fulfill actual Start timing as Past Timing INS User update valid Craft Licence number that starts with SB and leave Craft Name blank | 1. INS Bunkering was saved successfully 2. Check the updated bunkering info on Bunkering page (craft name and craft licence shown correctly, icon is in progress) 3. Check Dashboard still displays Green supporting vessel after updating craft info | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S77 | [Online - USW starts Supplies at Berth Location] - Update Actual Start timing |  | USW Supplies Svc Provider |  | USW User login to fulfill actual Start timing as Past Timing and Craft Name & Craft License Number | 1. USW Supplies was saved successfully 2. Check the updated Supplies info on Supplies page (icon changed to In progress) 3. Check Dashboard will display a Purple supporting vessel after fill in actual Start timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S78 | [Online - INS starts Bunkering at Anchorage Location] - Update Actual Start timing & Update both Craft Name and Craft Licence number |  | INS Bunkering Svc Provider |  | INS User login to fulfill actual Start timing as Past Timing INS updates valid Craft Name and leave Craft Licence number blank Note: - system can complete the information if it just has one of Craft Name or Craft Licence number | 1. INS Bunkering was saved successfully 2. Check the updated bunkering info on Bunkering page (icon changed to In progress) 3. Check Dashboard will display a Green supporting vessel after fill in actual Start timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S79 | [Online - USW starts Supplies at Anchorage Location] - Update Actual Start timing |  | USW Supplies Svc Provider |  | USW User login to fulfill actual Start timing as Past Timing and Craft Name & Craft License Number | 1. USW Supplies was saved successfully 2. Check the updated Supplies info on Supplies page (icon changed to In progress) 3. Check Dashboard will display a Purple supporting vessel after fill in actual Start timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S80 | [Online - Check all pages after ANU, INS, USW updated Actual Start Timing] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU BAS, AAU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 5 x Towage, 4 x Bunkering, 4 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) - ANU towage, INS Bunker, USW supplies having blue filled circle (i.e. in-progress), and all tugs info appear Vessel Itinerary Details - same info as vessel itinerary Start time of updated ANU towage and INS bunker activities changed Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record ) Circle in blue filled for ANU towage, INS Bunker, USW supplies. Supporting vessels have 2 Bunkering (green icon), 8 Towage (blue icon), 2 Supplies (purple icon) icon appeared (Note: Bunkering & Supplies Supporting Vessel: when [Craft Licence Number exist] + current time fall in [Actual Start > Planned > CST > SRT - 1hr(config) until actual end time] Towage Supporting Vessel: when [Craft Licence Number exist] + current time fall in [CST/Actual start time - 1hr(config) until actual end time]) Status = In Port, ATB: 26 Mar 2023 14:32 (P10) ETU: 31 Mar 2023 09:59 (P10) Katalon pages comparison for INS, BAS, ANU, AAU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S81 | [Online - ANU completes Towage Order] - Update Actual End timing with 4 Tugs info |  | ANU Towage Svc Provider |  | ANU User login to fulfill actual End timing as past timing after check the Icon on dashboard, then update Actual End timing | ANU Towage was saved successfully Check the updated Towage info on Towage page (icon changed to Blue filled icon means Completed) Check Dashboard the Blue supporting vessel will disappear after fill in Actual End Timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S82 | [Online - INS completes Bunkering at Berth Location] - Update Actual End timing |  | INS Bunkering Svc Provider |  | INS User login to fulfill actual End timing as past timing | INS Bunkering was saved successfully Check the updated bunkering info on Bunkering page (icon changed to green filled icon means Completed) Check Dashboard the Green supporting vessel will disappear after fill in Actual End Timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S83 | [Online - USW completes Supplies at Berth Location] - Update Actual End timing |  | USW Supplies Svc Provider |  | USW User login to fulfill actual End timing as past timing | USW Supplies was saved successfully Check the updated Supplies info on Supplies page (icon changed to green filled icon means Completed) Check Dashboard the Purple supporting vessel will disappear after fill in Actual End Timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S84 | [Online - INS completes Bunkering at Anchorage Location] - Update Actual End timing |  | INS Bunkering Svc Provider |  | INS User login to fulfill actual End timing as past timing | INS Bunkering was saved successfully Check the updated bunkering info on Bunkering page (icon changed to green filled icon means Completed) Check Dashboard the Green supporting vessel will disappear after fill in Actual End Timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S85 | [Online - USW completes Supplies at Anchorage Location] - Update Actual End timing |  | USW Supplies Svc Provider |  | USW User login to fulfill actual End timing as past timing | USW Supplies was saved successfully Check the updated Supplies info on Supplies page (icon changed to green filled icon means Completed) Check Dashboard the Purple supporting vessel will disappear after fill in Actual End Timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S86 | [Online - BAS completes Bunkering at Anchorage Location] - Update Planned Start and Planned End timing, Actual Start and Actual End timing and Craft Name & Licence |  | BAS Bunkering Svc Provider |  | BAS User login to fulfill Planned Start and Planned End timing, Actual Start and Actual End timing as past timing, Craft Name & Licence | INS Bunkering was saved successfully Check the updated bunkering info on Bunkering page (icon changed to green filled icon means Completed) | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S87 | [Online - YCP completes Supplies at Anchorage Location] - Update Actual Start and Actual End timing and Craft Name & Licence |  | YCP Supplies Svc Provider |  | YCP User login to fulfill Planned Start and Planned End timing, Actual Start and Actual End timing as past timing, Craft Name & Licence | USW Supplies was saved successfully Check the updated Supplies info on Supplies page (icon changed to green filled icon means Completed) | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S88 | [Online - Check all pages after ANU, INS, USW updated Actual End Timing] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU BAS, AAU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 5 x Towage, 4 x Bunkering, 4 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) ANU towage, INS Bunker, USW supplies having green ticked circle (i.e. Completed), and all tugs info disappeared Vessel Itinerary Details - same info as vessel itinerary End time of ANU towage, INS Bunker and USW Supplies updated Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) Circle in green filled for ANU towage, INS Bunker, USW supplies. No more Supporting vessels shown Status = In Port, ATB: 26 Mar 2023 14:32 (P10) ETU: 31 Mar 2023 09:59 (P10) Katalon pages comparison for INS, BAS, ANU, AAU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S89 | [Online - Vessel Itinerary Details, after ANU, INS, USW activities completed] - click on Envelope |  | CCA Agent Ship Master |  | Agent click on Envelope | Message "Email sent successful" appeared Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S90 | Verify the History online when activities updated |  | PMP |  | 1. Check above updated Activities via online 2. Check above updated Activities via DB | 1. Check Vessel Itinerary Details Page under activities should display the correct info in history 2. Check DB history table should exist records with history activities. | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S91 | [Online - Vessel Itinerary Details, Delete Bunkering at Berth Location activity] - to BAS |  | CCA Agent |  | Agent User login, go to Vessel Itinerary Details to delete Bunkering at Berth Location activity Do not save | The deleted BAS Bunkering activity disappeared from Vessel Itinerary Details page | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S92 | [Online - Vessel Itinerary Details, Delete Towage activity] - to AAU |  | CCA Agent |  | Continue in Vessel Itinerary Details: Delete Towage activity Do not save | The deleted AAU Towage activity disappeared from Vessel Itinerary Details page | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S93 | [Online - Vessel Itinerary Details, Delete Supplies at Berth Location activity] - to YCP |  | CCA Agent |  | Continue in Vessel Itinerary Details: Delete Supplies at Berth activity Do not save | The deleted YCP Supplies activity disappeared from Vessel Itinerary Details page | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S94 | [Online - Vessel Itinerary Details, Delete Bunkering at Anchorage Location activity] - to BAS |  | CCA Agent |  | Continue in Vessel Itinerary Details: Delete Bunkering at Anchorage Location activity Do not save | The deleted BAS Bunkering activity disappeared from Vessel Itinerary Details page | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S95 | [Online - Vessel Itinerary Details, Delete Supplies at Anchorage Location activity] - to YCP |  | CCA Agent |  | Continue in Vessel Itinerary Details: Delete Supplies at Anchorage Location activity Do not save | The deleted YCP Supplies activity disappeared from Vessel Itinerary Details page | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S96 | [Online - Agent Save Vessel Itinerary] - after Delete click SAVE |  | CCA Agent |  | 1. Agent click Save button | After Save the Vessel Itinerary display submit Successfully and back to Vessel Itinerary page with all records refreshed. Agent check Vessel Itinerary Page The Deleted activities disappear from Vessel Itinerary page | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S97 | [Online - Check all pages after BAS, AAU, YCP activities deleted] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU BAS, AAU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 4 x Towage, 2 x Bunkering, 2 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) AAU towage, BAS Bunker, YCP supplies info disappeared Vessel Itinerary Details - same info as vessel itinerary AAU towage, BAS Bunker, YCP supplies deleted Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) Status = In Port, ATB: 26 Mar 2023 14:32 (P10) ETU: 31 Mar 2023 09:59 (P10) BAS Check Bunkering Page and AAU Check Towage Page No Vessel listed as the activities was deleted Katalon pages comparison for INS, ANU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S98 | [Online - Vessel Itinerary Details, after activities update] - click on Envelope |  | CCA Agent Ship Master |  | Agent click on Envelope | Message "Email sent successful" appeared Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S99 | [Online & DB ] - History after activities Delete BAS, AAU, YCP |  | PMP |  | 1. DB check above BAS, AAU, YCP Activities history via SQL | 1. Check DB history table should not exist records in the activities parent and child tables. | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S100 | [Online Download - only assigned Service provider BAS Bunkering Activity can be Downloaded] |  | BAS Supplies Svc Provider |  | Service Provider Download Supplies activity in Bunkering Page | Check the download CSV only exist own company records (note: the deleted records will not be download) | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S101 | [Online Upload - Display Bunkering when Upload Edit CSV: CST, Plan Start, Plan End not within Suggest Activities Duration] |  | Bunkering Svc Provider |  | Service Provider Upload Bunkering activity in Bunkering Page - Bunkering at Berth Location & at Anchorage Location all exist - the upload the CSV with CST, Plan Start, Plan End not within Suggest Activities Duration | Error will prompt for Cannot upload with CST, Plan Start, Plan End not within Suggest Activities Duration | [11 empty] | V2.15 2023 DEC
TC_PSAC_S102 | [Online Upload - Upload BAS Bunkering CSV , CST, Plan Start, Plan End and Actual Timing] |  | BAS Supplies Svc Provider |  | Service Provider Change CSV , CST, Plan Start, Plan End and Actual Timing of Bunkering and then Upload the CSV | Check Bunkering Page all information uploaded correctly as CSV | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S103 | [Online Download - only assigned Service provider AAU Towage Activity can be Downloaded] |  | AAU Towage Svc Provider |  | Service Provider Download Towage activity in Towage Page | Check the download CSV only exist own company records (note: the deleted records will not be download) | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S104 | [Online Upload - Upload AAU Towage CSV , CST, Actual Timing] |  | AAU Towage Svc Provider |  | Service Provider Change CSV , CST, Plan Start, Plan End and Actual Timing of Towage and then Upload the CSV | Check Towage Page all information uploaded correctly as CSV | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S105 | [Online Download - only assigned Service provider YCP Supplies Activity can be Downloaded] |  | YCP Supplies Svc Provider |  | Service Provider Download Supplies activity in YCP Supplies Page | Check the download CSV only exist own company records (note: the deleted records will not be download) | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S106 | [Online Upload - Display Supplies when Upload Edit CSV: CST, Plan Start, Plan End not within Suggest Activities Duration] |  | Bunkering Svc Provider |  | Service Provider Upload Bunkering activity in Supplies Page - Supplies at Berth Location & at Anchorage Location all exist - the upload the CSV with CST, Plan Start, Plan End not within Suggest Activities Duration | Error will prompt for Cannot upload with CST, Plan Start, Plan End not within Suggest Activities Duration | [11 empty] | V2.15 2023 DEC
TC_PSAC_S107 | [Online Upload - Upload YCP Supplies CSV , CST, Plan Start, Plan End and Actual Timing] |  | YCP Supplies Svc Provider |  | Service Provider Change CSV , CST, Plan Start, Plan End and Actual Timing of YCP Supplies and then Upload the CSV | Check Supplies Page all information uploaded correctly as CSV | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S108 | [DPP2 API - Update Terminal Data record SEQ1 ATU] - SEQ1 (Location P10) |  | PSA Terminal | Prepare Data | 1. Craft Update Terminal JSON message and run in Postman - Execute JSON for Seq1 first Note: If ATU is past timing (current-6) , notification won't be trigger for outdated 6 hours. | 1. Terminal Data for SEQ1 ATU updated successfully. | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S109 | [Online - Check all pages after Update SEQ1 ATU] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 4 x Towage, 2 x Bunkering, 2 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Header's Unberthing time = ATU Unberthing activity end time = ATU Unberthing green ticked (i.e. completed) Vessel Itinerary Details - same info as vessel itinerary Actual Time of Unberthing = ATU Unberthing End timing = ATU Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record) Status = In Port, ATB: 26 Mar 2023 14:32 (P10) ETU: 31 Mar 2023 09:59 (P10) Katalon pages comparison for INS, ANU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S110 | [Online - Vessel Itinerary Details, after ATU update] - click on Envelope |  | CCA Agent Ship Master |  | Agent click on Envelope | Message "Email sent successful" appeared Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S111 | [Email - Notification after ATU update] - ATU exist |  | CCA Agent and Svc Providers (INS, ANU) |  | Check Agent and Service Provider email note: (current time - 6hrs) <ATB/ATU< current time | Message "Email sent successful" appeared Terminal ATU first creation will sent 1 mail to ship agent and count of activities ORGC mails to Service Provider [JIT] Vessel ATU | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S112 | [DPP2 API - Start Pilotage Service Outbound] - Update Start Time and Arrival Date. No end time - OrderNumber is same with Pilotage Order | Pilotage onboard | Service Provider PSAM |  | DPP2 API - Update Outbound Pilotage Service for P10 to SEAW - Update Onboard Date and Start Time, No end time - "adviceC": "A" | 1. Pilotage Service for Outbound Pilotage Order updated successfully via API 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S113 | [DPP2 API - Start Towage Service Outbound] - Update Start Time, and add in 4 tugs details. No end time - OrderNumber is same with Towage Order |  | Service Provider PSAM |  | DPP2 API- Update Outbound Towage Service for P10 to SEAW - Update Start Time, and add in 4 tugs details. No end - "adviceC": "U" | 1. Towage Order for Outbound updated successfully via API 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 3. Check Dashboard will display an Blue supporting vessel for the 4 Tugs after fill in the actual Start Time | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S114 | [Online - Check all pages after Outbound Pilotage & Towage started] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 4 x Towage, 2 x Bunkering, 2 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Updated Pilotage and Towage have blue filled icon (in-progress), start time updated Vessel Itinerary Details - same info as Vessel Itinerary Pilot Onboard Time (Outbound) updated Pilotage and Towage actual start timings updated Dashboard - vessel displayed and all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record ) Circle in blue filled for towage (OUT) n pilotage (OUT). Supporting vessels have 4 towage icon appeared Status = Departing, POB (OUT): 07 Mar 2023 13:10 Katalon pages comparison for INS, ANU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S115 | [Online - Vessel Itinerary Details, after Outbound Pilotage & Towage updated] - click on Envelope |  | CCA Agent Ship Master |  | Agent click on Envelope | Message "Email sent successful" appeared Agent & Ship master will receive email notification - 2 mails' All the information with all activities exist in the email are correct. - [JIT] Vessel Itinerary - Vessel name | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S116 | [DPP2 API - Complete Pilotage Service Outbound] - Update End Time - OrderNumber is same with Pilotage Order | Pilotage onboard | Service Provider PSAM |  | DPP2 API - Update Outbound Pilotage Service for P10 to SEAW - Update End Time - "adviceC": "A" | 1. Pilotage Service for Outbound Pilotage Order updated successfully via API 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 | [10 empty] | S | V2.15 2023 DEC
TC_PSAC_S117 | [DPP2 API - Complete Towage Service Outbound] - Update 4 tugs End Time - OrderNumber is same with Towage Order |  | Service Provider PSAM |  | DPP2 API - Update Outbound Towage Service for P10 to SEAW - Update End Time - "adviceC": "U" | 1. Towage Order for Outbound updated successfully via API 2. all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 3. Check Dashboard the Blue supporting vessel for the 4 Tugs will disappear after fill in Actual End Timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S118 | [Online - Check all pages after Outbound Pilotage & Towage completed] Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers + Katalon comparison for all SP pages with Agent Vessel Itinerary (must match exactly) |  | CCA Agent INS, ANU |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Dashboard for Service Providers Run Katalon | Vessel Itinerary Page (1 x Berthing, 1 x Unberthing, and all dates, 3dot > Edit AND Delete, 2 x Pilotage, 4 x Towage, 2 x Bunkering, 2 x Supplies, Activity sorting correct) All activity with service provider shown correctly All activity is sorted correctly based on its priority (Actual timing > Planned timing > CST > SRT) Outbound Pilotage and Towage alert icons become green filled, end time updated Vessel Itinerary Details - same info as Vessel Itinerary Pilot End Time (Outbound) updated Pilotage and Towage actual end timing updated Dashboard - all activities icon and info sequence display correct. (Check status, Check listing of activities, can collapse the vessel record ) Status = Departing, POB (OUT): 07 Mar 2023 13:10 Katalon pages comparison for INS, ANU with Agent Vessel Itinerary - ALL screen information matched, i.e. Katalon result = PASSED | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S119 | [DB - Update RTD date is within 3 days ] - Update RTD with past timing within 3 days (e.g. current - 1 day) and BE Job will not update departed_i, i.e. still remain as 'N' | [DB - Update RTD and departed_i = Y , Batch job = ON] | MPA MDH |  | Update RTD with past timing within 3 days (e.g. current - 1 day) and BE Job will not update departed_i, i.e. still remain as 'N' refer to DB SQL Sheet | RTD was updated successfully Note: BE job will look at RTD leave it as 'N' within 3days, once timing is More than 3 days it will set departed_i to 'Y' immediately the display of all pages is following the departed_i status only (Y / N). When 'N', all pages can still display, when 'Y' none displayed. | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S120 | [Online - Check all pages after RTD exist and departed_i = 'N'] - Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent - Check Supplies, Towage, Bunkering Page for Service Providers - Dashboard will show the Port Stay information as RTA until RTD duration (days hrs mm) |  | MPA MDH |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Supplies, Towage, Bunkering Page for Service Providers | Vessel Itinerary - Vessel still been displayed, but no 3dot Vessel Itinerary Details - no longer available Dashboard - still can display (Estimated Port Stay is showing the correct timing difference between RTA and RTD) Service Providers screen - can only Edit Actual timing , cannot edit CST & Planned timing | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S121 | [DB - Update RTD to outside 3 days] - Update RTD with past timing more than 3 days ,(e.g. current - 4 days) and BE Job will set departed_i to 'Y' automatically |  | MPA MDH |  | Update RTD with past timing more than 3 days ,(e.g. current - 4 days) and BE Job will set departed_i to 'Y' automatically refer to DB SQL Sheet | RTD was updated successfully | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S122 | [Online - Check all pages after RTD exist and departed_i = 'Y'] - Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent - Check Supplies, Towage, Bunkering Page for Service Providers |  | MPA MDH |  | Check Vessel Itinerary, Vessel Itinerary Details, Dashboard for Agent Check Supplies, Towage, Bunkering Page for Service Providers | Vessel Itinerary - Vessel can no longer be retrievable Vessel Itinerary Details - no longer available Dashboard - no longer available Service Providers screen - Vessel can no longer be retrievable | [10 empty] | M | V2.15 2023 DEC
TC_PSAC_S123 | [ Check userId & orgC for all acidities created based on above test cases from DB table of DPP2 ] |  | PSAC Terminal |  | Check CREATOR_ID and CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C for all acidities based on above test cases from DB table of DPP2 | all CREATOR_ORG_C,MODIFIER_ID,MODIFIER_ORG_C same with DPP2 - endpoint.xlsx linked in Sheet Ref for V2.10 note: for MODIFIER_ID,MODIFIER_ORG_C upon creation is empty but shortly after the creation email is send out it will become PCSYS as the BE batch job update the record with the notifyEtb_dt fields | [10 empty] | M | V2.15 2023 DEC